## Sheet1
GOALS: Desired outcomes to fulfill mission & realize vision | OBJECTIVES: Measurable, time limited results leading to achievement of goals | STRATEGIES: General description of actions you will take to achieve goals | TACTICS: To implement strategies: How, what, where, by whom
Goal 1: Healthy Organization | **This April, 2023 goal will be update by December, 2025
Goal: Protection
We support the legal and long-term protection of wild places and waters by preventing or mitigating harmful activities and safeguarding these environments for their ecological, recreational, and cultural value.
Rails to Trails
| 1. By April 2025 transfer NITU to Trust for Public Lands. | A. Obtain Status of Request for Substitution from STB | Call or email; Nancy
| 2. By Sept 2025 determine TCWP fund-raising needs. | A. Meet monthly with Oneida Echos group & Tom Lamb | A. Nancy and Mark will meet monthly with local Oneida group beginning immediately after STB issues opinion.
| 3. By Dec 2025 work with Oneida Group to garner three county support | A. Establish teams to work within each county. B. Establish process and people to approach to garner support in each county. | A. and B. By May 31, 2025 TCWP meets with local Oneida group to determine who in each group will constitute each county team, what process will be used to appoach which people in each county.
| 4. By Dec 2025 facilitate an agreement of roles, responsibilities, and ownership of the trail in collaboration with Oneida Group and TPL. | A. TCWP proposes roles and responsibilities to present to local Oneida group. B. Identiy of permanent owner of line established by Dec. 2025. | A. Based upon May meeting, Nancy develops roles and responsibilites by July, 2025 and presents to local Oneida group in next monthly meeting. B. At monthly meetings, each county group checks in with viability of determining perm. owner.
Pellissippi Blueway
| 1. By Dec 2025 co-host at least one cleanup event on the Blueway. | A. At one of monthly Blueway meetings, set up a date for this and decide who will coordinate event, what promotion will be needed and which platforms will be used, who will be responsible for promotion, who will be leaders for event, who will take photos during event to promote post event. | A. Jimmy and Chuck
| 2. By December 2026, TCWP will actively support the Pellissippi Blueway coalition by contributing to at least three key project components: a) help plan for and develop access points to include signage that includes education, history, environmental features b) Aid in surveying and identifying potential invasive plant species at appropriate Blueway access locations and tagging invasive plants for removal; help plan for and provide volunteers to engage in invasive removal at identified access points and c) help plan for prevention of erosion at boat ramps. | A. Attend monthly Blueway meetings. B. Share this Objective with Allison Bullock to confirm this Objective is workable. C. Bring this Objective to monthly Blueways meetings to establish a timeline and to develop teams within the Blueway partnership to implement these key components. | A. Nancy and Mark alternate attending monthly meetings. B. Nancy will take Objective to April 15th Blueway meeting per Chuck. C. Nancy will meet with Chuck to establish timeline and logistics.
Obed WSR
| 1. By December 2025, ensure all our properties have a clear title. | A. Review Regulations of the Attorney General Governing the Review and Approval of Title for Federal Land Acquisitions to determine what will constitute clear title. Compare title of our properties to required Regulations. | A. Jacob reviews regulations and compares our titles.
| 2. By December 2025 track the status of TCWP properties for transfer to NPS. | A. Contact regional NPS officer to request status. | A. Nancy calls regional officer by May 31, 2025.
| 3. By Dec 2025 finalize trade/ purchase of Beasley property and initiate sale to NPS | A. Ensure funds available and engage title company to finalize sale | A. Nancy tracks status of grant and if not received in April, initiates fundraising campaing from individual donors by April 30, 2025. B. Nancy will reach out to board for help if grant not received.
| 4. By Dec 2025 work with NPS - BSF/OBED to update list of interested properties for purchase or conservation easement | A. Schedule Face-to-face or site meetings with NPS-BSF/Obed/Manhattan 2-3 times per year to identify needs and opportunities for land acquisition for long-term protection.
| 5. By Dec 2025 work with Tenn Green to complete purchase of land at Jett Bridge/Clear Creek. | A. Contact Alice Pell to determine what we can do | A. By May 1, Nancy will contact Alice.
Statewide Land Protection
| 1. Annually identify needs, opportunities and collaborators for land acquisition for long term protection focused in East TN | A. By Aug 2025 create a database of partners we have collaborated with in the past 10 years, including 1) names and contact info of those people we currently communicate with, 2) issues we worked on, and 3) which TCWP member(s) engaged with the partner. B. Once every six months, send out email to collaborators requesting whether there is land acquisition opportunities. | A. Use upcoming board meetings to generate a list of past collaborating organizations and other potential new collaborators. Mark. B. Nancy will email requests to potential collaborators.
Oak Ridge Reservation
| 1. By Dec 2025 work with AFORR to establish roles and priorities for TCWP to support protection of natural resources on the ORR. | A. Determine who will be representatives from TCWP and AFORR and set up an intitial meeting re: roles / priorities and determine if site visits needed and possible. | Jimmy and Nancy will discuss at an AFORR meeting to decide who on AFORR board will work on this. A. After discussed, AFORR decided we should meet with City quite soon so Nancy will send out email to relevant potential team members and Ellen will contact relevant City personnel.
Gas Pipeline
| 1. By April 2025 meet with Obed Superintendent to understand and collaborate on Material Requirements and 3rd Party Inspections. | A. Prepare for meeting with Niki (review Section 7 opinion) and plan for discussions - what do we want to walk away with?
| 2. By Dec 2025 establish our oversight/monitoring role with Ridgeline Voices group to monitor actions of the pipeline construction and the environmental monitoring contractor. | A. Hold a meeting with key folks from Ridgeline Voices and the MVP group to establish monitoring that will align with what learned from Niki | A. By April 30, 2025 Nancy will determine who can conduct training for citizen science monitoring at critical water crossings. Ridgeline voices will get a map of critical crossings. B. By August, of 2025 Nancy will meet with Ridgeline voices to implement plan for monitoring
| 3. By September, 2025 hold awareness event at Lilly Pad. | A. Set out in writing, key roles and responsibilities for the event and how will implement. | A. Nancy will continue to meet with Ridgeline Voices through date of event on September 5th.
EMDF
| 1. By Dec 2025 stay engaged with landfill working group by attending monthly meetings and providing updates to TCWP membership in bi-monthly newsletters with calls to actions as appropriate. | A. Attend EMDF meetings 2 times per month and summarize meetings to compile into a report by the September board meeting. Turn reports into articles for newsletter. | Nancy will continue to represent TCWP in the regular zoom meetings.
West End Oak Ridge industrial development
| 1. Create a committee to evaluate development in this area and report back to the board by August 2025 as to whether there are actions that TCWP needs to consider. | A. Nancy will develop an e-blast and FB post to engage folks to join said committee and will also ask the AFORR group. | Once members of committee are identified, Nancy will set up first zoom meeting in June, 2025 to determine needs for information, monitoring, assignment of roles, etc.
Goal: Advocacy
We seek to effect positive change in policy, public opinion and community action through developing partnerships, strategies and programs to ensure the enduring protection and sustainable management of wild places and waters .
Direct Lobbying
| 1. In February of 2026, TCWP sends lobbyist to Nashville and letters to legislators on bills the committee has selected for action | A. By August 2025, define roles and responsibilities of legislative committee and process by which board will interact with that committee. B. By September, 2025, promote need for legislative committee within our network and community to attend legislative sessions, review specific bills and summarize for board decision making. C. By November 2025, define process by which TCWP will develop and distribute fact sheets. D. By February of 2026, Board will decide which categories of bills the committee can take action on. | A. Nancy will start role/ responsibility document in early August for board review at August board meeting. B. Nancy will provide Peyten with info for promotion in Sept. C. Nancy will set up first meeting of committee in October of 2025 that will be a first training of what happens during session, will discuss how to review/summarize bills and best prep for 2026 session. D. Nancy will meet with committee re: fact sheets and how to prepare for providing BOD with bills needing action
Grassroots Lobbying
| 1. By June 2025, TCWP will develop and maintain a Rapid Response Advocacy Alert System (email + social media + web update protocols) to notify members within 24 hours of urgent legislative action needed. | A. As part of web development, Nancy will obtain advice from web developer of how best to set this up on website using Sierra Club and SELC examples. B.. Nancy and Eva will work with Peyten to establish a protocol | Nancy, Eva, Peyten
| 2. TCWP will alert at least 300 members to submit constituent messages to legislators during the 2026 legislative session in response to urgent alerts. | A. Prior to legislative session, the legislative committee will work with the communications team to establish talking points and email samples for specific bills identified by committee. B. The legislative committee will develop a list of legislators relevant committees which will include email and phone numbers. | The legislative committee will watch the dates by which legislators are assigned to their committees and begin developing the list of reps of what is believed to be the critical committees.
| 3. By December 2025, TCWP will identify partners and location to host an in-person training to equip members and the community with effective advocacy tools, including how to call/write legislators and track bills. | A. Nancy will develop this training and be prepared to deliver it by early January with identified partners (Scott of Sierra Club) and include a zoom option. | Nancy will work with Scott Banbury of Sierra Club to develop this training and promote it to Club and TCWP members and others.
Public Education
| 1. TCWP will produce and distribute at least six educational pieces (e.g., newsletters, blog posts, fact sheets, or webinars) by the end of 2025 that inform the public about major local and state advocacy issues (e.g., EMDF dump, wetlands, nuclear expansion). | A. Nancy will continue to review Google Alerts for relevant issues (but would be nice to have help!) and will continue to summarize for newsletter. B. Nancy will ensure that relevant blogs are created for issues needing a Call to Action along with social media posts that link to blog and e-blasts that link to blog. | Schedule is set for 6 issues per year beginning in January. Advocacy Communications a. Newsletter- Produce 6 newsletters a year with content that encourages TCWP members to take advocacy actions b. Peyten will design and add action alerts to blogs, eblasts, social media.
| 2. By November of 2025, Hold a a joint event to educate people about the political process related to conservation or wilderness protection (e.g., a presentation given at the Oak Ridge Public Library in coonjunctive with a civic minded organization and/ or by a professor of political sciences). | A. In the summer of 2025, reach out to potential partners and presenters and work together in the planning process. | Nancy and Hans and newly formed legislative committee
Coalition Building
| 1. By July of 2025 visit with current Conservation Day on the Hill partners to become a partner. | A. Nancy will reach out to partners but will advise of development of committee. B. Maintain membership and active involvement in state-wide advocacy organizations such as the Tennessee Conservation Voters and the Primacy Group (change of groups)
3. Stewardship
We actively care for and protect natural environments and water resources by conducting and supporting activities that ensure the long-term health, sustainability, and conservation of these ecosystems.
Plant Community Management
| 1. By December 2025, conduct at least 5 plant community management workdays at Cedar Barrens, Worthington Cemetery, Wildflower Greenway, engaging at least 150 volunteers. | A. During the November, 2025 program committee meeting, attempts will be made to establish the workdays for 2026. | Program Committee
| 2. By December 2025, identify 1 additional plant community management opportunity to support or conduct engaging new collaborating groups. | A. During the November, 2025 program committee meeting, suggestions will be sought for the additional opportunity. | Program Committee
| 3. By June 2026, review Cedar Barrens Management Plan and update as necessary. | A. Each member of group should review the current management plan and report back to group with suggested changes that need to be made to update the plan. Date for review and reports back should provide enough lead time to update plan by June of 2026. | Jimmy, Margaret, Larry.
| 4. By June 2026, obtain and review the TVA Management Plan for Worthington Cemetery and work with TVA if updates are needed. | A. Request copy of TVA Management Plan (summer of 2025?) and review same for needed changes. | Jimmy and TVA reps. Nancy will review cultural resources section with Ann Worthington.
| 5. By August of 2026, hold a bio-blitz for monitoring the health of the rare plant populations at Cedar Barrens. | A. Meeting to determine the scope of bio-blitz and monitoring protocol by September, 2025. B. Communications team will collaborate with bio-blitz team to determine promotion needed. | Jimmy, Larry, Margaret and ??? Nancy and communications team
Trail Maintenance & Ecosystem Conservation
| 1. By December 2025, complete at least 4 trail maintenance projects (e.g., erosion control, signage updates, clearing obstructions, invasive species removal) across North Ridge Trail, Alley Ford, White’s Creek, East Fork Poplar Creek Trail engaging 40 volunteers. | A. Identify a lead person for each of these activities so that they can organize early with collaborators (if applicable). B. Produce timely promotion. | A. Program Committee B. Nancy and Peyten
3. Education
By fostering a sense of understanding, responsibility, and passion for the protection of wild places and waters, our education programs aim to inform, inspire, and empower individuals and communities to become active participants in the preservation of natural environments and water resources.
Public Education: Nature Outings
| 1. By December 2025, host at least eight guided nature outings, engaging at least 200 participants in hands-on learning about local ecosystems, conservation issues, and outdoor recreation. | A. During the November, 2025 program committee meeting, attempts will be made to establish the guided nature hikes for 2026. | Program committee
| 2. By June 2026, develop and implement a post-event survey for all nature outings, achieving at least a 70% response rate and using feedback to refine future programming. (survey includes plant knowledge and how they will use it personally; qualitative questions about inspiration). | A. Meeting with Nancy, Margaret, Erin, Jimmy, Larry to draft survey | Nancy, Erin, Margaret, Jimmy, Larry
| 3. By June 2026, develop an “After Action Review” for outing leaders to assess the success of the outing and write a brief summary for newsletter. | A. Meeting with Nancy, Margaret, Erin, Jimmy, Larry to adopt standard After Action Review. | Margaret, Jimmy, Larry, Erin.
| 4. By December 2026, collaborate with at least three partners (e.g., local businesses, educational institutions, or other conservation groups) to expand the reach and impact of the nature outings. | A. Nancy will set up a meeting with Communications Team to determine messaging and platforms needed. B. Team will decide which collaborators will be approached and who will approach | Communications Team
| 5. By June 2026, assess for update the 2 kiosks at Cedar Barrens to enhance visitor education and navigation. | A. Determine what is needed to update the kiosks, who will make determination and evaluate if location should be changed somewhat. | Jimmy and ????
Youth Education: Explore and Restore Program
| 1. By June of 2025, complete implementation of the Robertsville Explore and Restore Program. | A. Dates currently scheduled
| 2. By June of 2025, conduct an “After Action Review” of E & R program. | A. On last day of E & R program, leaders will choose date of conduct review or will conduct it on the final date of E & R program | Margaret, Larry, Jimmy, Nancy, Mark, Stephanie Sluss
| 3. By August of 2025, develop a curriculum for the Explore and Restore program that aligns with Tennessee Academic Standards. | A. All leader participants shall meet in August (at Margaret's house to watch the baby sleep!) to develop this curriculum together. | Margaret, Larry, Jimmy, Nancy, Mark, Stephanie Sluss
Community Engagement & Awareness
| 1. By December 2025, create and launch at least three new educational materials (e.g., videos, brochures, online resources, presentations) that highlight key conservation topics and TCWP. | A. Youtube and Linkedin will be developed and promoted. Development shall be design and content based. | Communications Team will determin content. Peyten will work on design
| 2. By June of 2026, evaluate the viability of a Conservation on Tap program, Lunch and Learn or similar social / educational event. | A. Compile a list of the organizations that TCWP has presented to in the past 8 or 10 years (including who presented and when). B. Identify businesses and organizations that provide lunch and learn programs in Oak Ridge | Mark, Nancy and Hans
| 3. By June 2026, conduct a specialized outing or event for engaging new members. | A. Program Committee and Communications Team will meet to decide upon an outing or event to engage new members, including location, details, etc. | Communications Team and Program Committee
| 4. By June 2026, identify opportunities for events or outings that educate on specific threats. | A. Program committee will work to identify one specific threat that would be available for a visit and determine if permission would be needed, set a date for the outing, determine a leader. Promotion would be encouraged. | Program committee and communications team.